## Site Clearing
67c5096331b15f75545b7b7a
Productivity Matrix
Project name
Oran Park Resi 3
Address
62 Central Ave, Oran Park
As of 4:12am, Monday 30th June
Completion 0.00%
ID | Hold | Type | Task | Progress
6850aa889d6b0c8289d9833a |  |  | Site Clearing | / | /
6850aa889d6b0c8289d9833e | FALSE | Task | Prepare Site access and egress for excavation/ shoring | 0 | 2025-07-29
6850aa889d6b0c8289d98345 | FALSE | Task | Survey set up and Setout (Grid lines, Offsets & BM's) | 0 | 2025-07-30

## Piling Stage
685099229d6b0c82896f8864
Productivity Matrix
Project name
Oran Park Resi 3
Address
62 Central Ave, Oran Park
As of 4:12am, Monday 30th June
Completion 0.00%
ID | Hold | Type | Task | Progress
6850aa889d6b0c8289d9834c |  |  | Piling Pour 1 | / | /
6850aa889d6b0c8289d98350 | FALSE | Task | Survey and Set Out Piles | 0 | 2025-07-30
6850aa889d6b0c8289d98358 | FALSE | Task | Piling Drilling | 0 | 2025-07-30
6850aa889d6b0c8289d9835f | FALSE | Task | Installation of Pile Reinforcement | 0 | 2025-07-31
6850aa889d6b0c8289d98366 | TRUE | Task | Geotechnical and Structural Engineer Inspection (HOLD POINT) | 0 | 2025-07-31
6850aa889d6b0c8289d9836d | TRUE | Task | Complete Piling ITC / Action Plan (HOLD POINT) | 0 | 2025-08-01
6850aa889d6b0c8289d98374 | FALSE | Task | Concrete Place to Piles | 0 | 2025-08-01
6850aa889d6b0c8289d9837c |  |  | Piling Pour 2 | / | /
6850aa889d6b0c8289d98380 | FALSE | Task | Survey and Set Out Piles | 0 | 2025-08-01
6850aa889d6b0c8289d98388 | FALSE | Task | Piling Drilling | 0 | 2025-08-01
6850aa889d6b0c8289d9838f | FALSE | Task | Installation of Pile Reinforcement | 0 | 2025-08-04
6850aa889d6b0c8289d98396 | TRUE | Task | Geotechnical and Structural Engineer Inspection (HOLD POINT) | 0 | 2025-08-04
6850aa889d6b0c8289d9839d | TRUE | Task | Complete Piling ITC / Action Plan (HOLD POINT) | 0 | 2025-08-05
6850aa889d6b0c8289d983a4 | FALSE | Task | Concrete Place to Piles | 0 | 2025-08-05
6850aa889d6b0c8289d983ac |  |  | Piling Pour 3 | / | /
6850aa889d6b0c8289d983b0 | FALSE | Task | Survey and Set Out Piles | 0 | 2025-08-05
6850aa889d6b0c8289d983b8 | FALSE | Task | Piling Drilling | 0 | 2025-08-05
6850aa889d6b0c8289d983bf | FALSE | Task | Installation of Pile Reinforcement | 0 | 2025-08-06
6850aa889d6b0c8289d983c6 | TRUE | Task | Geotechnical and Structural Engineer Inspection (HOLD POINT) | 0 | 2025-08-06
6850aa889d6b0c8289d983cd | TRUE | Task | Complete Piling ITC / Action Plan (HOLD POINT) | 0 | 2025-08-07
6850aa889d6b0c8289d983d4 | FALSE | Task | Concrete Place to Piles | 0 | 2025-08-07
6850aa889d6b0c8289d983dc |  |  | Piling Pour 4 | / | /
6850aa889d6b0c8289d983e0 | FALSE | Task | Survey and Set Out Piles | 0 | 2025-08-08
6850aa889d6b0c8289d983e8 | FALSE | Task | Piling Drilling | 0 | 2025-08-08
6850aa899d6b0c8289d983ef | FALSE | Task | Installation of Pile Reinforcement | 0 | 2025-08-09
6850aa899d6b0c8289d983f6 | TRUE | Task | Geotechnical and Structural Engineer Inspection (HOLD POINT) | 0 | 2025-08-09
6850aa899d6b0c8289d983fd | TRUE | Task | Complete Piling ITC / Action Plan (HOLD POINT) | 0 | 2025-08-11
6850aa899d6b0c8289d98404 | FALSE | Task | Concrete Place to Piles | 0 | 2025-08-12

## Capping Beam Stage
685099319d6b0c82896f8882
Productivity Matrix
Project name
Oran Park Resi 3
Address
62 Central Ave, Oran Park
As of 4:12am, Monday 30th June
Completion 0.00%
ID | Hold | Type | Task | Progress
6850aa899d6b0c8289d9840c |  |  | Capping Beam Pour 1 | / | /
6850aa899d6b0c8289d98410 | FALSE | Task | Survey and Setout Capping Beam | 0 | 2025-08-13
6850aa899d6b0c8289d98418 | FALSE | Task | Capping Beam Formwork and Reinforcment Place | 0 | 2025-08-14
6850aa899d6b0c8289d9841f | TRUE | Task | Structural Engineer Inspection (HOLD POINT) | 0 | 2025-08-15
6850aa899d6b0c8289d98426 | TRUE | Task | Complete Capping Beam ITC / Action Plan (HOLD POINT) | 0 | 2025-08-15
6850aa899d6b0c8289d9842d | FALSE | Task | Concrete Place to Capping Beam | 0 | 2025-08-15
6850aa899d6b0c8289d98435 |  |  | Capping Beam Pour 2 | / | /
6850aa899d6b0c8289d98439 | FALSE | Task | Survey and Setout Capping Beam | 0 | 2025-08-13
6850aa899d6b0c8289d98441 | FALSE | Task | Capping Beam Formwork and Reinforcment Place | 0 | 2025-08-16
6850aa899d6b0c8289d98448 | TRUE | Task | Structural Engineer Inspection (HOLD POINT) | 0 | 2025-08-17
6850aa899d6b0c8289d9844f | TRUE | Task | Complete Capping Beam ITC / Action Plan (HOLD POINT) | 0 | 2025-08-17
6850aa899d6b0c8289d98456 | FALSE | Task | Concrete Place to Capping Beam | 0 | 2025-08-17
6850aa899d6b0c8289d9845e |  |  | Capping Beam Pour 3 | / | /
6850aa899d6b0c8289d98462 | FALSE | Task | Survey and Setout Capping Beam | 0 | 2025-08-15
6850aa899d6b0c8289d9846a | FALSE | Task | Capping Beam Formwork and Reinforcment Place | 0 | 2025-08-18
6850aa899d6b0c8289d98471 | TRUE | Task | Structural Engineer Inspection (HOLD POINT) | 0 | 2025-08-19
6850aa899d6b0c8289d98478 | TRUE | Task | Complete Capping Beam ITC / Action Plan (HOLD POINT) | 0 | 2025-08-19
6850aa899d6b0c8289d9847f | FALSE | Task | Concrete Place to Capping Beam | 0 | 2025-08-19
6850aa899d6b0c8289d98487 |  |  | Capping Beam Pour 4 | / | /
6850aa899d6b0c8289d9848b | FALSE | Task | Survey and Setout Capping Beam | 0 | 2025-08-15
6850aa899d6b0c8289d98493 | FALSE | Task | Capping Beam Formwork and Reinforcment Place | 0 | 2025-08-20
6850aa899d6b0c8289d9849a | TRUE | Task | Structural Engineer Inspection (HOLD POINT) | 0 | 2025-08-21
6850aa899d6b0c8289d984a1 | TRUE | Task | Complete Capping Beam ITC / Action Plan (HOLD POINT) | 0 | 2025-08-21
6850aa8a9d6b0c8289d984a8 | FALSE | Task | Concrete Place to Capping Beam | 0 | 2025-08-21

## Excavation and Shoring
6850abc19d6b0c8289df6e81
Productivity Matrix
Project name
Oran Park Resi 3
Address
62 Central Ave, Oran Park
As of 4:12am, Monday 30th June
Completion 0.00%
ID | Hold | Type | Task | Progress
6850c0ea9d6b0c8289f19f39 |  |  | Pour 1 | / | /
6850c0ea9d6b0c8289f19f3d | FALSE | Task | First Drop Excavation and Shoring | 0 | 2025-09-03
6850c0ea9d6b0c8289f19f45 | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-08-29
6850c0ea9d6b0c8289f19f4c | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-08-30
6850c0ea9d6b0c8289f19f53 | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-08-31
6850c0ea9d6b0c8289f19f5a | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-09-01
6850c0ea9d6b0c8289f19f61 | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-09-01
6850c0ea9d6b0c8289f19f68 | FALSE | Subtask | 6 Anchoring | 0 | 2025-09-03
6850c0ea9d6b0c8289f19f6f | FALSE | Task | Second Drop Excavation and Shoring | 0 | 2025-09-15
6850c0ea9d6b0c8289f19f76 | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-09-09
6850c0ea9d6b0c8289f19f7d | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-09-10
6850c0ea9d6b0c8289f19f84 | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-09-11
6850c0ea9d6b0c8289f19f8b | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-09-12
6850c0ea9d6b0c8289f19f92 | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-09-12
6850c0ea9d6b0c8289f19f99 | FALSE | Subtask | 6 Anchoring | 0 | 2025-09-15
6850c0ea9d6b0c8289f19fa0 | FALSE | Task | Third Drop Excavation and Shoring | 0 | 2025-09-18
6850c0ea9d6b0c8289f19fa7 | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-09-14
6850c0ea9d6b0c8289f19fae | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-09-15
6850c0ea9d6b0c8289f19fb5 | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-09-16
6850c0ea9d6b0c8289f19fbc | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-09-18
6850c0ea9d6b0c8289f19fc3 | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-09-18
6850c0ea9d6b0c8289f19fcb |  |  | Pour 2 | / | /
6850c0ea9d6b0c8289f19fcf | FALSE | Task | First Drop Excavation and Shoring | 0 | 2025-09-11
6850c0ea9d6b0c8289f19fd7 | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-09-06
6850c0ea9d6b0c8289f19fde | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-09-07
6850c0ea9d6b0c8289f19fe5 | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-09-08
6850c0ea9d6b0c8289f19fec | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-09-09
6850c0ea9d6b0c8289f19ff3 | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-09-09
6850c0ea9d6b0c8289f19ffa | FALSE | Subtask | 6 Anchoring | 0 | 2025-09-11
6850c0ea9d6b0c8289f1a001 | FALSE | Task | Second Drop Excavation and Shoring | 0 | 2025-09-23
6850c0ea9d6b0c8289f1a008 | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-09-18
6850c0ea9d6b0c8289f1a00f | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-09-19
6850c0ea9d6b0c8289f1a016 | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-09-20
6850c0ea9d6b0c8289f1a01d | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-09-21
6850c0ea9d6b0c8289f1a024 | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-09-20
6850c0ea9d6b0c8289f1a02b | FALSE | Subtask | 6 Anchoring | 0 | 2025-09-23
6850c0ea9d6b0c8289f1a032 | FALSE | Task | Third Drop Excavation and Shoring | 0 | 2025-09-26
6850c0ea9d6b0c8289f1a039 | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-09-22
6850c0ea9d6b0c8289f1a040 | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-09-23
6850c0ea9d6b0c8289f1a047 | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-09-24
6850c0ea9d6b0c8289f1a04e | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-09-25
6850c0ea9d6b0c8289f1a055 | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-09-26
6850c0ea9d6b0c8289f1a05d |  |  | Pour 3 | / | /
6850c0ea9d6b0c8289f1a061 | FALSE | Task | First Drop Excavation and Shoring | 0 | 2025-09-19
6850c0ea9d6b0c8289f1a069 | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-09-15
6850c0ea9d6b0c8289f1a070 | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-09-15
6850c0eb9d6b0c8289f1a077 | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-09-16
6850c0eb9d6b0c8289f1a07e | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-09-17
6850c0eb9d6b0c8289f1a085 | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-09-18
6850c0eb9d6b0c8289f1a08c | FALSE | Subtask | 6 Anchoring | 0 | 2025-09-19
6850c0eb9d6b0c8289f1a093 | FALSE | Task | Second Drop Excavation and Shoring | 0 | 2025-09-27
6850c0eb9d6b0c8289f1a09a | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-09-22
6850c0eb9d6b0c8289f1a0a1 | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-09-23
6850c0eb9d6b0c8289f1a0a8 | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-09-24
6850c0eb9d6b0c8289f1a0af | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-09-25
6850c0eb9d6b0c8289f1a0b6 | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-09-26
6850c0eb9d6b0c8289f1a0bd | FALSE | Subtask | 6 Anchoring | 0 | 2025-09-27
6850c0eb9d6b0c8289f1a0c4 | FALSE | Task | Third Drop Excavation and Shoring | 0 | 2025-10-01
6850c0eb9d6b0c8289f1a0cb | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-09-26
6850c0eb9d6b0c8289f1a0d2 | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-09-27
6850c0eb9d6b0c8289f1a0d9 | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-09-29
6850c0eb9d6b0c8289f1a0e0 | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-09-30
6850c0eb9d6b0c8289f1a0e7 | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-10-01
6850c0eb9d6b0c8289f1a0ef |  |  | Pour 4 | / | /
6850c0eb9d6b0c8289f1a0f3 | FALSE | Task | First Drop Excavation and Shoring | 0 | 2025-09-27
6850c0eb9d6b0c8289f1a0fb | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-09-22
6850c0eb9d6b0c8289f1a102 | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-09-23
6850c0eb9d6b0c8289f1a109 | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-09-24
6850c0eb9d6b0c8289f1a110 | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-09-25
6850c0eb9d6b0c8289f1a117 | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-09-26
6850c0eb9d6b0c8289f1a11e | FALSE | Subtask | 6 Anchoring | 0 | 2025-09-27
6850c0eb9d6b0c8289f1a125 | FALSE | Task | Second Drop Excavation and Shoring | 0 | 2025-10-08
6850c0eb9d6b0c8289f1a12c | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-10-02
6850c0eb9d6b0c8289f1a133 | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-10-03
6850c0eb9d6b0c8289f1a13a | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-10-04
6850c0eb9d6b0c8289f1a141 | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-10-06
6850c0eb9d6b0c8289f1a148 | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-10-07
6850c0eb9d6b0c8289f1a14f | FALSE | Subtask | 6 Anchoring | 0 | 2025-10-08
6850c0eb9d6b0c8289f1a156 | FALSE | Task | Third Drop Excavation and Shoring | 0 | 2025-10-11
6850c0eb9d6b0c8289f1a15d | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-10-07
6850c0eb9d6b0c8289f1a164 | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-10-08
6850c0eb9d6b0c8289f1a16b | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-10-09
6850c0eb9d6b0c8289f1a172 | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-10-10
6850c0eb9d6b0c8289f1a179 | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-10-11
6850c0eb9d6b0c8289f1a181 |  |  | Pour 5 | / | /
6850c0eb9d6b0c8289f1a185 | FALSE | Task | First Drop Excavation and Shoring | 0 | 2025-10-08
6850c0eb9d6b0c8289f1a18d | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-10-02
6850c0eb9d6b0c8289f1a194 | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-10-03
6850c0eb9d6b0c8289f1a19b | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-10-04
6850c0eb9d6b0c8289f1a1a2 | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-10-06
6850c0eb9d6b0c8289f1a1a9 | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-10-07
6850c0eb9d6b0c8289f1a1b0 | FALSE | Subtask | 6 Anchoring | 0 | 2025-10-08
6850c0eb9d6b0c8289f1a1b7 | FALSE | Task | Second Drop Excavation and Shoring | 0 | 2025-10-16
6850c0eb9d6b0c8289f1a1be | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-10-10
6850c0eb9d6b0c8289f1a1c5 | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-10-11
6850c0eb9d6b0c8289f1a1cc | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-10-13
6850c0eb9d6b0c8289f1a1d3 | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-10-14
6850c0eb9d6b0c8289f1a1da | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-10-15
6850c0eb9d6b0c8289f1a1e1 | FALSE | Subtask | 6 Anchoring | 0 | 2025-10-16
6850c0ec9d6b0c8289f1a1e8 | FALSE | Task | Third Drop Excavation and Shoring | 0 | 2025-10-20
6850c0ec9d6b0c8289f1a1ef | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-10-15
6850c0ec9d6b0c8289f1a1f6 | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-10-16
6850c0ec9d6b0c8289f1a1fd | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-10-17
6850c0ec9d6b0c8289f1a204 | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-10-18
6850c0ec9d6b0c8289f1a20b | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-10-20
6850c0ec9d6b0c8289f1a213 |  |  | Pour 6 | / | /
6850c0ec9d6b0c8289f1a217 | FALSE | Task | First Drop Excavation and Shoring | 0 | 2025-10-16
6850c0ec9d6b0c8289f1a21f | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-10-10
6850c0ec9d6b0c8289f1a226 | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-10-11
6850c0ec9d6b0c8289f1a22d | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-10-13
6850c0ec9d6b0c8289f1a234 | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-10-14
6850c0ec9d6b0c8289f1a23b | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-10-15
6850c0ec9d6b0c8289f1a242 | FALSE | Subtask | 6 Anchoring | 0 | 2025-10-16
6850c0ec9d6b0c8289f1a249 | FALSE | Task | Second Drop Excavation and Shoring | 0 | 2025-10-24
6850c0ec9d6b0c8289f1a250 | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-10-20
6850c0ec9d6b0c8289f1a257 | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-10-20
6850c0ec9d6b0c8289f1a25e | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-10-21
6850c0ec9d6b0c8289f1a265 | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-10-22
6850c0ec9d6b0c8289f1a26c | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-10-23
6850c0ec9d6b0c8289f1a273 | FALSE | Subtask | 6 Anchoring | 0 | 2025-10-24
6850c0ec9d6b0c8289f1a27a | FALSE | Task | Third Drop Excavation and Shoring | 0 | 2025-10-28
6850c0ec9d6b0c8289f1a281 | FALSE | Subtask | 1 Bulk Excavation | 0 | 2025-10-23
6850c0ec9d6b0c8289f1a288 | FALSE | Subtask | 2 Preparing Shoring Wall Reinforcement | 0 | 2025-10-24
6850c0ec9d6b0c8289f1a28f | TRUE | Subtask | 3 Structural Engineer Inspection (HOLD POINT) | 0 | 2025-10-25
6850c0ec9d6b0c8289f1a296 | TRUE | Subtask | 4 Complete Shoring ITC / Action Plan (HOLD POINT) | 0 | 2025-10-27
6850c0ec9d6b0c8289f1a29d | FALSE | Subtask | 5 Shotcrete / Concrete Place to Shoring Walls | 0 | 2025-10-28

## Footings and Foundation Piles
6850c18e9d6b0c8289f53f37
Productivity Matrix
Project name
Oran Park Resi 3
Address
62 Central Ave, Oran Park
As of 4:12am, Monday 30th June
Completion 0.00%
ID | Hold | Type | Task | Progress
686203caa3aa316b80c8fb8c |  |  | Tower Crane | / | /
686203caa3aa316b80c8fb90 | FALSE | Task | Survey | 0 | 2025-08-02
686203caa3aa316b80c8fb98 | FALSE | Task | Excavate to Crane Base | 0 | 2025-08-04
686203caa3aa316b80c8fb9f | FALSE | Task | Reinforcement Place to Crane Base | 0 | 2025-08-05
686203caa3aa316b80c8fba6 | TRUE | Task | Geotechnical and Structural Engineer Inspection (HOLD POINT) | 0 | 2025-08-05
686203caa3aa316b80c8fbad | TRUE | Task | Complete Crane Base ITC / Action Plan (HOLD POINT) | 0 | 2025-08-05
686203caa3aa316b80c8fbb4 | FALSE | Task | Concrete Place to Crane Base | 0 | 2025-08-06
686203caa3aa316b80c8fbbb | FALSE | Task | Curing Period for Crane Base 1 | 0 | 2025-09-03
686203caa3aa316b80c8fbc2 | FALSE | Task | Erect Crane & Commission | 0 | 2025-10-30
686203caa3aa316b80c8fbca |  |  | Pour 1 | / | /
686203caa3aa316b80c8fbce | FALSE | Task | Survey of Piles and Lift Base | 0 | 2025-09-19
686203caa3aa316b80c8fbd6 | FALSE | Task | Excavation of Piles and Lift Base | 0 | 2025-09-23
686203caa3aa316b80c8fbdd | TRUE | Task | Geotechnical Engineer Inspection (HOLD POINT) | 0 | 2025-09-24
686203caa3aa316b80c8fbe4 | FALSE | Task | Reinforcment Place of Piles and Lift Base | 0 | 2025-09-24
686203caa3aa316b80c8fbeb | TRUE | Task | Structural Engineer Inspection (HOLD POINT) | 0 | 2025-09-25
686203caa3aa316b80c8fbf2 | TRUE | Task | Complete Pile / Footing ITC / Action Plan (HOLD POINT) | 0 | 2025-09-25
686203caa3aa316b80c8fbf9 | TRUE | Task | Concrete Place of Lift Base and Piles | 0 | 2025-09-29
6862078aa3aa316b80cca382 |  |  | Pour 2 | / | /
6862078aa3aa316b80cca386 | FALSE | Task | Survey of Piles, Pile Caps and Lift / Stair Base | 0 | 2025-09-29
6862078aa3aa316b80cca38d | FALSE | Task | Excavation of Piles, Pile Caps and Lift Base | 0 | 2025-10-04
6862078aa3aa316b80cca393 | TRUE | Task | Geotechnical Engineer Inspection (Hold Point) | 0 | 2025-10-06
6862078aa3aa316b80cca399 | FALSE | Task | Reinforcment Place of Piles, Pile Caps and Lift Base | 0 | 2025-10-07
6862078aa3aa316b80cca39f | TRUE | Task | Structural Engineer Inspection (Hold Point) | 0 | 2025-10-08
6862078aa3aa316b80cca3a5 | TRUE | Task | Complete Pile / Footing ITC / Action Plan (HOLD POINT) | 0 | 2025-10-08
6862078aa3aa316b80cca3ab | FALSE | Task | Concrete Place of Piles, Pile Caps and Lift Base | 0 | 2025-10-09
6862078aa3aa316b80cca3b2 |  |  | Pour 3 | / | /
6862078aa3aa316b80cca3b6 | FALSE | Task | Survey of Piles, Pile Caps and Lift / Stair Base | 0 | 2025-10-08
6862078ba3aa316b80cca3bd | FALSE | Task | Excavation of Piles, Pile Caps and Lift Base | 0 | 2025-10-13
6862078ba3aa316b80cca3c3 | TRUE | Task | Geotechnical Engineer Inspection (Hold Point) | 0 | 2025-10-13
6862078ba3aa316b80cca3c9 | FALSE | Task | Reinforcment Place of Piles, Pile Caps and Lift Base | 0 | 2025-10-14
6862078ba3aa316b80cca3cf | TRUE | Task | Structural Engineer Inspection (Hold Point) | 0 | 2025-10-15
6862078ba3aa316b80cca3d5 | TRUE | Task | Complete Pile / Footing ITC / Action Plan (HOLD POINT) | 0 | 2025-10-15
6862078ba3aa316b80cca3db | FALSE | Task | Concrete Place of Piles, Pile Caps and Lift Base | 0 | 2025-10-16
6862078ba3aa316b80cca3e2 |  |  | Pour 4 | / | /
6862078ba3aa316b80cca3e6 | FALSE | Task | Survey of Piles, Pile Caps and Lift / Stair Base | 0 | 2025-10-13
6862078ba3aa316b80cca3ed | FALSE | Task | Excavation of Piles, Pile Caps and Lift Base | 0 | 2025-10-17
6862078ba3aa316b80cca3f3 | TRUE | Task | Geotechnical Engineer Inspection (Hold Point) | 0 | 2025-10-18
6862078ba3aa316b80cca3f9 | FALSE | Task | Reinforcment Place of Piles, Pile Caps and Lift Base | 0 | 2025-10-21
6862078ba3aa316b80cca3ff | TRUE | Task | Structural Engineer Inspection (Hold Point) | 0 | 2025-10-22
6862078ba3aa316b80cca405 | TRUE | Task | Complete Pile / Footing ITC / Action Plan (HOLD POINT) | 0 | 2025-10-22
6862078ba3aa316b80cca40b | FALSE | Task | Concrete Place of Piles, Pile Caps and Lift Base | 0 | 2025-10-23
6862078ba3aa316b80cca412 |  |  | Pour 5 | / | /
6862078ba3aa316b80cca416 | FALSE | Task | Survey of Piles and Stair Base | 0 | 2025-10-21
6862078ba3aa316b80cca41d | FALSE | Task | Excavation of Piles, Stair Base and Stormwater Pump Out Pit | 0 | 2025-10-25
6862078ba3aa316b80cca423 | TRUE | Task | Geotechnical Engineer Inspection (Hold Point) | 0 | 2025-10-25
6862078ba3aa316b80cca429 | FALSE | Task | Reinforcment Place of Piles, Stair Base and Stormwater Pump Out Pit | 0 | 2025-10-29
6862078ba3aa316b80cca42f | TRUE | Task | Structural Engineer Inspection (Hold Point) | 0 | 2025-10-30
6862078ba3aa316b80cca435 | TRUE | Task | Complete Pile / Footing ITC / Action Plan (HOLD POINT) | 0 | 2025-10-30
6862078ba3aa316b80cca43b | FALSE | Task | Concrete Place of Stair Base, Stormwater Pump Out Pit and Piles | 0 | 2025-10-31
6862078ba3aa316b80cca442 |  |  | Pour 6 | / | /
6862078ba3aa316b80cca446 | FALSE | Task | Survey of Piles and Stair Base | 0 | 2025-10-29
6862078ba3aa316b80cca44d | FALSE | Task | Excavation of Piles and Stair Base | 0 | 2025-11-01
6862078ba3aa316b80cca453 | TRUE | Task | Geotechnical Engineer Inspection (Hold Point) | 0 | 2025-11-01
6862078ba3aa316b80cca459 | FALSE | Task | Reinforcment Place of Piles and Stair Base | 0 | 2025-11-04
6862078ca3aa316b80cca45f | TRUE | Task | Structural Engineer Inspection (Hold Point) | 0 | 2025-11-05
6862078ca3aa316b80cca465 | TRUE | Task | Complete Pile / Footing ITC / Action Plan (HOLD POINT) | 0 | 2025-11-06
6862078ca3aa316b80cca46b | FALSE | Task | Concrete Place of Stair Base and Piles | 0 | 2025-11-07